## Risks
risk_id | title | asset | threat | vulnerability | owner | likelihood | impact | controls | treatment | treatment_plan | due_date | residual_likelihood | residual_impact | approved_by
R-001 | Leaver accounts not disabled | Directory and core payment system accounts | A former employee or contractor signs in with a still-active account | Offboarding is manual and not linked to the HR leaver event | Head of IT Operations | 4 | 4 | 5.18, 6.5, 5.16 | mitigate | Disable accounts automatically from the HR leaver event; weekly reconciliation report | 2026-09-15 | 2 | 3
R-002 | No periodic user access review | Core payment system access rights | Access rights accumulate and are never challenged | No scheduled recertification of who has which role | Compliance Officer | 3 | 4 | 5.15, 5.18, 8.2 | mitigate | Quarterly access recertification signed by each system owner | 2026-11-30 | 2 | 3
R-003 | Shared administrator accounts | Server and database administrator accounts | Administrator actions cannot be attributed to a person | Admin passwords are shared in a team spreadsheet | Head of IT Operations | 4 | 4 | 5.16, 5.17, 8.2 | mitigate | Named admin accounts with a password vault and session logging | 2026-12-15 | 2 | 3
R-004 | Excessive privileges in the core payment system | Core payment system roles | An operator misuses rights to release or alter payments | Roles are broad; operators can both prepare and release payments | Head of Payments Operations | 3 | 5 | 5.15, 8.2, 5.3 | mitigate | Redesign roles around least privilege and remove unused rights | 2027-01-31 | 2 | 4
R-005 | Phishing leads to credential theft | Staff mailboxes and SSO accounts | Phishing e-mail captures staff credentials | MFA is not enforced everywhere and awareness training is annual only | CISO Dana Whitcombe <dana.whitcombe@larkspur.example> | 5 | 4 | 6.3, 8.5, 8.7 | mitigate | Phishing-resistant MFA for all staff, quarterly training and simulations | 2026-10-31 | 3 | 3
R-006 | Unpatched VPN appliance | Remote access VPN appliance | Attacker exploits a known vulnerability in the VPN appliance | Firmware is patched quarterly, with no emergency patch process | Network Engineering Lead | 4 | 5 | 8.8, 8.9, 8.20 | mitigate | Monthly patch window and a 72-hour emergency patch SLA for critical issues | 2026-09-30 | 2 | 3
R-007 | Backups never restore-tested | Payment database backups | Data cannot be recovered after a failure or corruption | Restores have never been tested end to end | Head of IT Operations | 3 | 5 | 8.13, 5.30 | mitigate | Quarterly documented restore test against the payment database | 2026-11-15 | 2 | 3
R-008 | Ransomware on file servers and endpoints | File servers and staff endpoints | Ransomware encrypts data and halts operations | Flat network, uneven endpoint protection, backups reachable from the domain | CISO Dana Whitcombe <dana.whitcombe@larkspur.example> | 3 | 5 | 8.7, 8.13, 8.22 | mitigate | Network segmentation, EDR on all endpoints, offline backup copy | 2027-02-28 | 2 | 4
R-009 | Cloud storage misconfiguration | Object storage holding settlement files | Settlement files are exposed publicly by a misconfigured bucket | No configuration baseline or automated checks on storage settings | Cloud Platform Lead | 3 | 4 | 5.23, 8.9 | mitigate | Policy-as-code checks that block public buckets; weekly drift scan | 2026-10-20 | 1 | 4
R-010 | Third-party payment processor outage | Card payment processor connection | The processor is unavailable and payments cannot be authorised | Single processor, no fallback route, weak contractual remedies | Head of Payments Operations | 3 | 4 | 5.19, 5.22, 5.30 | transfer | Transfer part of the loss through SLA credits and business interruption insurance; agree a fallback processor | 2027-01-15 | 3 | 3
R-011 | Weak security terms in vendor contracts | Contracts with ICT suppliers | A supplier incident affects Larkspur without contractual recourse | Older contracts lack security, audit and incident notification clauses | Head of Legal | 3 | 3 | 5.19, 5.20, 5.22 | mitigate | Standard security addendum; renegotiate the ten most critical suppliers | 2026-12-31 | 2 | 2
R-012 | Missing logging and monitoring | Core payment system and network logs | Malicious activity goes unnoticed for weeks | Logs stay on each host and nobody reviews them | CISO Dana Whitcombe <dana.whitcombe@larkspur.example> | 4 | 4 | 8.15, 8.16, 8.17 | mitigate | Onboard core systems to a central log platform with alerting and a review rota | 2027-03-15 | 2 | 3
R-013 | Insecure code in the merchant portal | Merchant portal application | Injection or access control flaws expose merchant data | No automated code scanning or security review before release | Head of Engineering | 4 | 4 | 8.28, 8.25, 8.29 | mitigate | Add SAST and dependency scanning to CI and a pre-release security test | 2026-11-30 | 2 | 3
R-014 | Test environments hold real card data | Test and staging databases | Real card numbers leak from weakly protected test systems | Production data is copied to test for debugging | Head of Engineering | 3 | 5 | 8.33, 8.11 | avoid | Stop copying production data; use a synthetic data generator and masking | 2026-09-01 | 1 | 1
R-015 | Lost or stolen laptops | Staff laptops | A laptop with company data is lost or stolen | Disk encryption is not enforced on all laptops | IT Service Desk Manager | 3 | 3 | 8.1, 7.9, 8.24 | mitigate | Enforce full-disk encryption and remote wipe through device management | 2026-10-05 | 1 | 3
R-016 | Insider fraud through missing segregation of duties | Payment initiation and approval workflow | One person creates and approves a fraudulent payment | Initiation and approval can be done by the same user | Head of Finance | 2 | 5 | 5.3, 5.15 | mitigate | Four-eyes approval for payments above a threshold, enforced in the system | 2026-12-01 | 1 | 5
R-017 | Distributed denial of service | Public payment API and website | A volumetric attack makes the payment API unavailable | Capacity depends on the ISP; no dedicated scrubbing service | CISO Dana Whitcombe <dana.whitcombe@larkspur.example> | 4 | 4 | 8.20, 8.6 | accept | Rely on ISP-level mitigation for now; revisit at the annual risk review |  | 4 | 4 | CEO Marta Ilves <marta.ilves@larkspur.example>
R-018 | Weak cryptographic key management | Encryption keys for card and customer data | Keys are exposed or lost, so data is exposed or unrecoverable | Keys are stored beside the data they protect with no rotation | Head of Engineering | 2 | 5 | 8.24 | mitigate | Move keys to a managed KMS or HSM with rotation and access logging | 2027-02-15 | 1 | 4
R-019 | Personal data kept longer than needed | Customer personal data stores | Excess personal data is exposed in a breach or breaks data protection rules | No retention schedule and no automated deletion | Data Protection Officer | 4 | 3 | 5.34, 8.10, 5.33 | mitigate | Approve a retention schedule and automate deletion for the main stores | 2027-01-31 | 2 | 2
R-020 | No incident response plan | Incident handling process | A security incident is handled late or badly | No documented plan, roles or contact tree; no exercises | CISO Dana Whitcombe <dana.whitcombe@larkspur.example> | 4 | 4 | 5.24, 5.25, 5.26 | mitigate | Write the incident response plan, assign roles and run a tabletop exercise | 2026-10-15 | 2 | 3
R-021 | Change management bypassed | Production change process | An unreviewed change breaks or compromises production | Emergency changes can be deployed without approval or later review | Head of Engineering | 3 | 4 | 8.32 | mitigate | Require a ticket and a second reviewer for all production changes; review emergency changes weekly | 2026-11-20 | 2 | 3
R-022 | Uncontrolled access to the server room | On-premises server room | An unauthorised person gets physical access to servers | A shared door code is used and entries are not logged | Facilities Manager | 2 | 4 | 7.2, 7.3 | mitigate | Badge access with entry logs and a monthly log review | 2026-08-31 | 1 | 3
R-023 | Misuse of privileged utility programs | Administrative tools on servers | An administrator uses a utility to bypass application controls | Utilities are available to all administrators | Head of IT Operations | 2 | 3 | 8.18 | accept | Utilities limited to the admin group and logged; remaining risk accepted |  | 2 | 3 | CISO Dana Whitcombe <dana.whitcombe@larkspur.example>
R-024 | Clock drift breaks log correlation | Servers and network devices | Events cannot be correlated across systems during an investigation | Not all devices synchronise to the same time source | Network Engineering Lead | 2 | 2 | 8.17 | accept | Remaining devices tolerated until the next refresh; remaining risk accepted |  | 2 | 2 | CISO Dana Whitcombe <dana.whitcombe@larkspur.example>